## Schedule
today — Jul 10
Project Schedule and Timeline (June to December 2026) | [9 empty] | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec
Reporting date: July 10, 2026. Milestone dates follow the signed Schedule of Deliverables. | [9 empty] | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase | ID | Task | Owner | Deliverable | Depends on | Start | End | Status | % Complete
WRITING
| W1 | Ch. 2 — Review of Related Literature | JD | Chapter 2 draft + verified reference catalog | — | 2026-06-01 | 2026-07-03 | Done | 100% | bar: Jun 1 to Jul 1
| W2 | Ch. 3 — Technical Background | JD | Chapter 3 draft, 11 equations, 7 figures | W1 | 2026-06-08 | 2026-07-03 | Done | 100% | bar: Jun 2 to Jul 1
| W3 | Bibliography (APA 7th) | JD | Alphabetized APA 7th reference list | W1 | 2026-06-22 | 2026-07-03 | Done | 100% | bar: Jun 4 to Jul 1
| W4 | Research objectives / statement of the problem | Both | Objectives + SOP section | — | 2026-06-22 | 2026-07-09 | Done | 100% | bar: Jun 4 to Jul 2
| W5 | Ch. 4 — Design and Methodology | MC | Chapter 4 draft, §4.1–4.10 | W2 | 2026-06-22 | 2026-07-10 | In progress | 85% | bar: Jun 4 to Jul 2
| W6 | Appendices (transmittal letter, instrument, SRS) + CV | Both | Appendix set + curricula vitae | W5 | 2026-07-08 | 2026-07-16 | Planned | 0% | bar: Jul 2 to Jul 3
| W7 | Ch. 1 — Introduction and Abstract | Both | Chapter 1 + abstract | W4 | 2026-07-08 | 2026-07-17 | Planned | 0% | bar: Jul 2 to Jul 3
| W8 | Proposal document draft (Ch. 1–4, refs, appendices, CV) | Both | Compiled proposal document | W6, W7 | 2026-07-15 | 2026-07-23 | Planned | 0% | bar: Jul 3 to Jul 4
| W9 | Ch. 5 — Results and Discussion | Both | Chapter 5 draft with evaluation tables | D3.4 | 2026-09-01 | 2026-09-15 | Planned | 0% | bar: Sep 1 to Sep 3
| W10 | Ch. 6 — Summary, Conclusions, Recommendations | Both | Chapter 6 draft | W9 | 2026-09-16 | 2026-10-31 | Planned | 0% | bar: Sep 3 to Oct 4
DEVELOPMENT
| D1 | Increment 1 | JD | Increment 1 Deliverables | W5 | 2026-07-01 | 2026-07-31 | Planned | 0% | bar: Jul 1 to Jul 4
| D2 | Increment 2 | JD | Increment 2 Deliverables | D1 | 2026-08-01 | 2026-08-31 | Planned | 0% | bar: Jun 1 to Dec 4
| D3 | Increment 3 | Both | Increment 3 Deliverables | D2 | 2026-08-25 | 2026-09-15 | Planned | 0% | bar: Aug 4 to Sep 3
| D4 | Increment 4 | MC | Increment 4 Deliverables | D3 | 2026-09-16 | 2026-10-15 | Planned | 0% | bar: Jun 1 to Dec 4
MILESTONES
| M1 | Signed Schedule of Deliverables | Both |  |  | 2026-06-26 | bar: Jun 4
| M2 | Chapter 2, Chapter 3 and Bibliography submitted | JD |  |  | 2026-07-03 | bar: Jul 1
| M3 | Research Objectives / Statement of the Problem | Both |  |  | 2026-07-09 | bar: Jul 2
| M4 | Chapter 4 Design and Methodology submitted | MC |  |  | 2026-07-10 | bar: Jul 2
| M5 | Appendices (transmittal, instrument, SRS) and CV | Both |  |  | 2026-07-16 | bar: Jul 3
| M6 | Chapter 1 and Abstract submitted | Both |  |  | 2026-07-17 | bar: Jul 3
| M7 | Proposal Document Draft Ch. 1–4 with refs, appendices, CV | Both |  |  | 2026-07-23 | bar: Jul 4
| M8 | Agreement Letter (with parent's signature) | Both |  |  | 2026-07-24 | bar: Jul 4
| M9 | 3 copies of Thesis Proposal Document + sworn and recommendation letter | Both |  |  | 2026-07-27 | bar: Jul 4
| M10 | **Thesis Proposal Defense** | Both |  |  | Mon–Wed 03–05-Aug-2026 | bar: Aug 1
| M11 | Submission of Rubric 1, 2.1 and 2.2 | Both |  |  | 2026-08-10 | bar: Aug 2
| M12 | Revised Thesis Document and Compliance Form | Both |  |  | 2026-08-14 | bar: Aug 2
| M13 | Conference | Both |  |  | 2026-10-13
| M14 | Hardbound Copy | Both |  |  | 2026-12-15 | bar: Dec 1 to Dec 2
| M15 | **Final Defense** | Both |  |  | 2026-12-28
CLOSEOUT
| C1 | Closeout Activities (Testing, Revision, Defense Prep) | Both | Final deliverables | W10, D4 | 2026-11-01 | 2026-12-20 | Planned | 0% | bar: Jun 1 to Dec 4
Completed
In progress
Planned
◆ | Milestone / deadline
Note. Bars show planned effort spans; diamonds show fixed submission deadlines. Development increments overlap the empirical chapters because Chapter 5 reports the evaluation produced by Increment 3.

## Consultations
Date | Adviser | Topic | Action items | Resolved?

## Helper
2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-07-01 | 2026-07-08 | 2026-07-15 | 2026-07-22 | 2026-08-01 | 2026-08-08 | 2026-08-15 | 2026-08-22 | 2026-09-01 | 2026-09-08 | 2026-09-15 | 2026-09-22 | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-11-01 | 2026-11-08 | 2026-11-15 | 2026-11-22 | 2026-12-01 | 2026-12-08 | 2026-12-15 | 2026-12-22
2026-06-07 | 2026-06-14 | 2026-06-21 | 2026-06-30 | 2026-07-07 | 2026-07-14 | 2026-07-21 | 2026-07-31 | 2026-08-07 | 2026-08-14 | 2026-08-21 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-30 | 2026-10-07 | 2026-10-14 | 2026-10-21 | 2026-10-31 | 2026-11-07 | 2026-11-14 | 2026-11-21 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-31